## 0.Overview
SWP391- Project AI Usage Report
Subject Code | SWP391
Subject Name | Software Project
Class Code | SE20A09
Semester | Spring 2025
Lecturer Name
Group Code | Group 1
Project Title | Sport Venue Booking System
List of Student
No | StudentCode | StudentName | Role In Group | AI Tool Usaged
1 | DE190967 | Nguyễn Xuân Huy | Leader | Claude, Gemini
2 |  |  | Member
3 |  |  | Member
4 |  |  | Member
5 |  |  | Member

## 1. Week 1
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1 | Requirement | System Module Breakdown | Claude | Proposed 6 modules: User Management, Venue Management, Booking & Reservation, Payment, Notification, Admin Dashboard. | Removed Payment module (out of sprint 1 scope). Split Venue Management into Venue Search and Venue Detail per actual SRS requirements. |  | 5 modules defined, 1 removed, 1 split into 2 | 4 | AI included Payment module without checking scope constraints. Suggested overly broad modules that needed refinement.
2 | Requirement | Use Case Identification | Claude | Identified 3 actors (Customer, Venue Owner, Admin) and 6 use cases: Search Venue, Book Venue, Cancel Booking, Manage Venue, Approve Venue, Generate Report. | Added missing use case "View Booking History" which AI omitted despite being a core SRS requirement. Adjusted relationship between Admin and Venue Owner actors. |  | 3 actors defined; 7 use cases finalized (1 added by student) | 4 | AI missed "View Booking History" use case — detected only after cross-checking with SRS checklist.
3 | Requirement | System Context & External Entities | Gemini | Listed external entities: Customer, Venue Owner, Admin, Payment Gateway, Email Service with basic data flows. | Removed Payment Gateway (out of scope). Added SMS Notification Service for OTP verification per lecturer requirement. Updated data flow labels to match SRS terminology. |  | 4 external entities finalized; 2 data flows adjusted | 3 | AI assumed payment integration was in scope. Data flow descriptions were too generic and did not match project-specific terminology.
4 | Requirement | Role-Based Access Control Definition | Claude | Listed permissions for Customer, Venue Owner, and Admin roles with suggested access levels for each feature. | Verified permissions against SRS. Removed some Admin privileges that were overly broad. Refined Venue Owner access to only their own venues, not others. |  | 3 roles defined; permission matrix completed; 2 over-permissions corrected | 4 | AI granted Admin unrestricted access to all data without considering data isolation constraints between Venue Owners.
5 | Requirement | Booking Availability Logic Design | Claude | Suggested fixed 1-hour time slot locking with database transactions and optimistic locking to prevent double booking. | AI misunderstood business requirement: system requires flexible duration (1–4 hours), not fixed slots. Updated algorithm to check time-range overlap instead of slot index. Added min/max duration validation rule. |  | Overlap-check algorithm redesigned; 2 validation rules added | 3 | AI defaulted to fixed-slot model common in simpler systems. Misinterpreted flexible-duration requirement — required full algorithm redesign.
6 | Requirement | Venue Approval Workflow Design | Gemini | Proposed 3-step flow: Submit → Pending Review → Approved/Rejected. Rejected venues receive notification and can resubmit. | Added "Request Revision" state between Pending and Rejected per SRS. Updated Activity Diagram to reflect: Submit → Pending → Request Revision / Approved / Rejected. |  | Workflow extended from 3 to 4 states; Activity Diagram updated | 4 | AI did not account for "Request Revision" state specified in SRS. Flow was oversimplified compared to actual business requirement.
7 | Planning | Team Task Assignment – Week 1 | Claude | Suggested assigning 2 members to Use Case, 1 to ER Diagram, 1 to UI Wireframe, 1 to Requirement doc based on equal distribution. | Reassigned 1 member from Use Case to ER Diagram support based on actual database experience. Added peer review buffer time per team workflow. Final plan was more effective. |  | 5 tasks assigned; 1 reassignment made; review buffer added | 4 | AI assigned tasks based on generic role distribution without knowledge of individual member skills.
8 | Planning | Sprint Planning – 8-week Roadmap | Claude | Proposed 4 equal sprints: Sprint 1 Analysis & Design, Sprint 2 Core Features, Sprint 3 Advanced Features, Sprint 4 Testing & Deployment. | Extended Sprint 1 by 0.5 week for SRS peer review. Merged testing into Sprint 3 to avoid end-of-project crunch. Updated Gantt chart accordingly. |  | 4 sprints planned; 1 sprint adjusted in duration; Gantt chart updated | 4 | AI proposed equal-length sprints without considering peer review overhead. Testing phase was isolated, which is impractical for iterative development.

## 2. Week n
No. | SDLC Phase | Task / Activity | AI Tool Used | AI Output | Student’s Validation / Modification | Evidence / Link | Quantitative Measure | Value Added (1-5) | Risks / Limitations Observed
1
2
3
4
5

## Instruction
Column | Description & How to Fill
No. | Sequential number of the log entry (1, 2, 3…).
SDLC Phase | Which phase of the project this AI usage belongs to (e.g., Requirement, Design, Implementation, Testing, Reporting).
Task / Activity | Specific task you used AI for (e.g., User Story Development, ERD Design, Workflow 1 Coding, Test Case Generation).
AI Tool Used | Name of the AI tool (e.g., ChatGPT, GitHub Copilot, Copilot X, Bard, CodeWhisperer).
AI Output | The actual output AI produced (summary only, e.g., “10 user stories generated”, “ERD with 6 entities”, “sample Spring Boot controller”).
Student’s Validation / Modification | How you validated or modified the AI output (e.g., “kept 5 user stories, rewrote 3”, “adjusted foreign keys”, “fixed syntax errors”, “refined test cases”).
Evidence / Link | Link to a shared Google Drive folder containing screenshots/videos of the AI chat session(s). Naming convention: GroupX_SessionY_Activity (e.g., Group5_Session2_UserStory.png). Each screenshot/videos must clearly show: prompt, AI response, and student follow-up.
Quantitative Measure | Numerical evidence of the contribution (e.g., number of user stories, number of entities, number of classes/methods, LOC, number of test cases).
Value Added (1-5) | Self-assessment of AI’s usefulness (1 = not useful, 5 = very useful).
Risks / Limitations Observed | What limitations or risks you observed when using AI (e.g., “generated irrelevant user stories”, “missing validation logic”, “incomplete test coverage”).